DIGITAL PLATFORM FOR

ELECTRIC TRUCK AFTERSALES & FLEET MANAGEMENT

Solo Founder Execution Plan — Claude Code + TrueNAS Home Lab

| Document Type | CTO Execution Roadmap |
| --- | --- |
| Version | 1.1 — March 2026 |
| Audience | Solo Founder |
| Development Mode | Claude Code (primary AI coding tool) |
| Dev Environment | Workstation + TrueNAS Scale home lab |
| Total Timeline | ~36 Weeks (3 Phases) |
| Estimated Cost | $45 – $608 / month |

| Phase 1 Documentation Platform Weeks 1 – 8 | Phase 2 Aftersales Portal Weeks 9 – 24 | Phase 3 FleetOS Foundation Weeks 25 – 36 |
| --- | --- | --- |

# Executive Summary

This document is the authoritative execution guide for building the EV Truck Digital Platform as a solo founder using AI coding tools. It translates the system architecture into actionable sprints across three phases, each with specific tasks, technology requirements, AI prompts, time estimates, and risk controls.

The overarching principle is ruthless prioritisation: ship customer-visible value every two weeks, keep infrastructure costs below $200/month until revenue justifies scaling, and let AI tools handle 60-70% of boilerplate so you can focus on product decisions and customer feedback.

## The Three-Phase Model

| Phase | Outcome | Key Milestones | Success Metric |
| --- | --- | --- | --- |
| Phase 1 Wks 1–8 | Documentation Portal Live | Docusaurus deployed, 3-language docs, Nginx + CI/CD | First customer reads a manual online |
| Phase 2 Wks 9–24 | Full Aftersales Portal | Auth, vehicles, warranty, parts, tickets | First warranty claim submitted digitally |
| Phase 3 Wks 25–36 | FleetOS MVP | MQTT broker, telemetry dashboard, fault alerts | Live vehicle data visible in browser |

| PHASE 1 | Documentation Platform Establish credibility, deploy live documentation, and prove the CI/CD pipeline — Weeks 1 to 8 |
| --- | --- |

Phase 1 has a single goal: get something live that a real customer can read. A working documentation portal signals technical maturity to early adopters, generates organic search traffic, and forces you to build the entire deployment pipeline — which every later phase will reuse. Nothing here is throwaway work.

## Phase 1 — Objectives

- Deploy a multilingual documentation portal (EN / ZH / ID) to a public URL

- Establish the complete infrastructure: DigitalOcean + Docker + Nginx + Cloudflare + GitHub Actions CI/CD

- Publish real content: User Manual, Troubleshooting Guide, Warranty Overview for your primary truck model

- Set up the Next.js application shell and NestJS API skeleton (used in Phase 2)

## Phase 1 — Required Technologies

| Layer | Technology | Purpose |
| --- | --- | --- |
| Documentation | Docusaurus 3 | Static site generator for multilingual, versioned technical docs |
| i18n | Docusaurus i18n (native) | localeDropdown navbar item renders EN/ZH/ID switcher automatically; no plugins needed |
| Search | Algolia DocSearch | Free for public docs; superior relevance over local search |
| Local Storage (dev) | MinIO (Docker on TrueNAS) | S3-compatible; identical API to DigitalOcean Spaces; zero code changes between dev and prod |
| Frontend Shell | Next.js 14 + TypeScript | App router, server components, shared with Phase 2 portal |
| Styling | TailwindCSS + shadcn/ui | Utility-first CSS; shadcn provides production-ready components instantly |
| API Skeleton | NestJS + Prisma + PostgreSQL | Module scaffolding done in Phase 1; endpoints filled in Phase 2 |
| Cache / Queue | Redis 7 (Docker) | Ready for Phase 2 session storage and job queues |
| Reverse Proxy | Nginx (Docker) | Routes docs.domain, app.domain, api.domain from a single server |
| CDN / WAF | Cloudflare Free | SSL, DDoS protection, edge caching, global performance |
| Hosting | DigitalOcean Droplet (4GB) | $24/month; Managed PostgreSQL $15/month |
| Secrets | Doppler (free) | Injects env vars into Docker containers without committing .env files |
| CI/CD | GitHub Actions | Auto-deploy on push to main; runs tests before deploying |
| Monitoring | Sentry (free tier) | Error tracking from day one; catches regressions early |

## Phase 1 — Sprint Breakdown

| Sprint | Tasks & Deliverables | Duration |
| --- | --- | --- |
| Sprint 0 Local Dev + Infrastructure Foundation | - Set up TrueNAS Scale home lab: deploy PostgreSQL, MinIO, Meilisearch as persistent Docker services - Create GitHub monorepo with Turborepo (apps/web, apps/api, apps/docs) - Write docker-compose.dev.yml for workstation: Next.js, NestJS, Docusaurus, Redis — connecting to TrueNAS LAN IP - Write docker-compose.prod.yml for DigitalOcean: nginx, nextjs, nestjs, redis, docusaurus - Configure MinIO bucket and access keys; verify @aws-sdk/client-s3 works against local MinIO - Create .env.local (TrueNAS IPs) and .env.production (DigitalOcean) with Doppler managing secrets - Provision DigitalOcean Droplet + Managed PostgreSQL + Spaces (production targets) - Configure Cloudflare DNS: docs.domain, app.domain, api.domain - Configure GitHub Actions deploy workflow: test → build → SSH deploy to DigitalOcean - Write CLAUDE.md at repo root with architecture conventions, stack overview, and documentation layer rules | 2 weeks |
| Sprint 1 Documentation Architecture + Content | - Scaffold three-layer documentation structure: _shared/_partials/, platforms/t7-{90,90l,134l,169l}/, applications/{arm-roll,dumper,compactor,sweeper}/, manuals/ - Create MDX prop components: SpecTable (batteryKwh, rangeKm, gvwKg, dims) and RangeTable - Write shared partials in English: hv-safety.mdx, charging-guide.mdx, daily-inspection.mdx, cab-controls.mdx, warranty-overview.mdx - Write platform specs for T7-90 and T7-134L (highest-priority models first) - Assemble first two product manuals: T7-134L Standard and T7-134L Dumper as MDX import files - Configure Docusaurus i18n with localeDropdown navbar switcher (EN/ZH/ID) - Use Claude Code to translate _shared/_partials/ to Chinese and Indonesian; verify MDX tags preserved - Apply for Algolia DocSearch; configure Meilisearch fallback in local dev - Deploy documentation to docs.yourdomain.com; verify language switcher works in all three locales | 2 weeks |
| Sprint 2 Next.js + NestJS Shell | - Scaffold Next.js 14 app with App Router, TypeScript, Tailwind, shadcn/ui - Create route groups: /(marketing) and /(app) within single Next.js project - Build marketing homepage: hero section, features overview, CTA - Scaffold NestJS API with Prisma ORM; run first migration on Managed PostgreSQL - Implement basic health check endpoint GET /api/health - Set up Swagger auto-documentation at /api/docs - Create shared packages/types package with common TypeScript interfaces - Set up TanStack Query and global API client in Next.js - Write unit test suite skeleton (Jest + Supertest for NestJS) | 2 weeks |
| Sprint 3 SEO, Analytics, Polish | - Add sitemap.xml and robots.txt to documentation and marketing sites - Add JSON-LD structured data to marketing pages (Organisation, Product) - Configure Plausible Analytics (self-hosted, GDPR-compliant) - Add meta tags and Open Graph images to all public pages - Performance audit: Lighthouse score >85 on all Phase 1 pages - Mobile responsiveness pass on documentation and marketing homepage - Set up Grafana + Prometheus monitoring stack in Docker Compose - Write PHASE_1_RETROSPECTIVE.md capturing learnings and updated estimates - Onboard first customer: share docs URL, collect feedback | 2 weeks |

## Phase 1 — AI Coding Prompts

🤖 AI CODING PROMPTS — PHASE 1

Prompt 1: Monorepo + CLAUDE.md Setup Create a Turborepo monorepo with three apps: apps/web (Next.js 14 App Router, TypeScript, Tailwind, shadcn/ui), apps/api (NestJS with Prisma and PostgreSQL), apps/docs (Docusaurus 3 with i18n for en/zh/id). Include a shared packages/types package with common TypeScript interfaces. Add a root package.json with turbo.json for parallel build commands. Also create a CLAUDE.md at repo root documenting: stack overview, NestJS module conventions, Prisma usage rules, response envelope format, and the three-layer doc architecture (_shared/_partials, platforms/, applications/, manuals/).

Prompt 2: Docker Compose Stack Write a docker-compose.prod.yml that runs: nginx (routing docs.domain, app.domain, api.domain), a Next.js app (port 3000), NestJS API (port 4000), Docusaurus static site (port 3001), Redis 7 Alpine, and Meilisearch. All services on a private Docker network. Nginx terminates SSL with certs from /etc/letsencrypt. Include healthcheck configs. Environment variables injected from .env file.

Prompt 3: GitHub Actions CI/CD Write a GitHub Actions workflow that: (1) runs npm test on push to main, (2) builds Docker images for web and api, (3) SSHs into a DigitalOcean Droplet using an SSH key stored in GitHub Secrets, (4) runs git pull and docker compose up -d --build, (5) runs docker system prune to clean up old images. Use appleboy/ssh-action. Fail the deploy if tests fail.

Prompt 4: Docusaurus i18n + Three-Layer Doc Structure Configure Docusaurus 3 for a multi-product EV truck platform. (1) Set up i18n with defaultLocale 'en' and additional locales 'zh' and 'id'; add a localeDropdown navbar item at position right — this gives the EN/ZH/ID switcher automatically. (2) Create the three-layer folder structure: docs/_shared/_partials/ for content shared across all T7 trucks, docs/platforms/t7-{90,90l,134l,169l}/ for battery-variant content, docs/applications/{arm-roll,dumper,compactor,sweeper}/ for body-type content, and docs/manuals/ for assembled product-specific imports. (3) Write SpecTable and RangeTable as MDX components with TypeScript props. (4) Configure sidebars.js with T7-90 and T7-134L categories each containing Standard, Arm Roll, Dumper, Compactor, and Sweeper subcategories. (5) Add a GitHub Actions step that runs docusaurus write-translations for both zh and id locales on push to main. Use brand colours navy #1A3557 and blue #2563EB.

Prompt 5: NestJS Module Scaffold Given this Prisma schema [paste schema], generate a complete NestJS module for the Vehicle entity including: vehicles.module.ts, vehicles.controller.ts with full CRUD REST endpoints plus GET /vehicles/:id/warranty, vehicles.service.ts with business logic and Prisma calls, create-vehicle.dto.ts and update-vehicle.dto.ts with class-validator decorators, a vehicle.response.dto.ts that never exposes sensitive fields, Swagger @ApiOperation and @ApiResponse decorators on every endpoint, and a RolesGuard that allows CUSTOMER to read own vehicles and ADMIN to read all. Follow the pattern in the existing users module.

## Phase 1 — Estimated Development Time

| Total Calendar Time | 8 weeks (4 x 2-week sprints) |
| --- | --- |

| Effective Dev Hours | ~160 hours (20 hrs/week solo founder) |
| --- | --- |

| AI Tool Leverage | ~60% of code generated by Claude Code (boilerplate, configs, translations, tests) |
| --- | --- |

| Human Focus Hours | ~64 hours on architecture decisions, content writing, customer feedback |
| --- | --- |

| Infrastructure Cost | $39/month (Droplet $24 + Managed DB $15) |
| --- | --- |

## Phase 1 — Deliverables

| ✓ | Public documentation portal live at docs.yourdomain.com with EN/ZH/ID content |
| --- | --- |
| ✓ | Marketing homepage live at yourdomain.com with lead capture form |
| ✓ | NestJS API skeleton deployed at api.yourdomain.com with health endpoint and Swagger docs |
| ✓ | CI/CD pipeline: automatic deployment on every push to main branch |
| ✓ | Full monitoring stack: Grafana dashboards, Prometheus metrics, Sentry error tracking |
| ✓ | First customer onboarded and reading documentation online |

## Phase 1 — Risks and Mitigation

| Risk | Severity | Impact | Mitigation |
| --- | --- | --- | --- |
| Content creation bottleneck | High | Delays documentation launch by 2-4 weeks | Write documentation in point form first; use Claude to expand to full prose. Prioritise 3 docs over 10 mediocre ones. |
| TrueNAS Docker service instability | Medium | Local PostgreSQL/MinIO unreachable; dev blocked | Pin Docker image versions in TrueNAS (never use :latest). Keep local DB backups in a second TrueNAS dataset. Use static LAN IP for TrueNAS via router DHCP reservation. |
| Docker networking issues on first deploy | Medium | Lost weekend debugging Nginx config | Test docker-compose.dev.yml on workstation first. Use proven nginx config templates. Validate locally before pushing to production. |
| Cloudflare SSL certificate issues | Medium | Site unreachable until resolved | Keep Certbot as backup. Cloudflare's flexible SSL mode works immediately while full SSL is configured. |
| Algolia DocSearch application rejected | Low | Search not available at launch | Meilisearch is already in the Docker stack as a fallback. Apply early; approval takes 1-2 weeks. |
| Turborepo monorepo complexity | Low | Build issues slow down development velocity | Start with separate package.json scripts and add Turborepo incrementally. Don't over-engineer the build system early. |

| PHASE 2 | Aftersales Portal Build the authenticated customer portal: vehicle registry, warranty management, parts catalog, service tickets — Weeks 9 to 24 |
| --- | --- |

Phase 2 is where the platform becomes a real product. Customers log in, register their trucks, check warranty status, search parts, and open service tickets. Internal engineers manage claims and respond to issues. This phase generates the first defensible moat: structured data about your vehicles in the field.

## Phase 2 — Objectives

- Complete user authentication with role-based access control (Customer, Service Partner, Engineer, Admin)

- Build vehicle registry: VIN-based registration, model specs, service history

- Build warranty management: active warranties, claim submission, engineer review workflow

- Build parts catalog: searchable, filterable, with compatibility matrix and inquiry flow

- Build service ticket system: creation, assignment, comments, file attachments, status notifications

- Build admin dashboard: user management, reporting, system health

## Phase 2 — Required Technologies

| Layer | Technology | Purpose |
| --- | --- | --- |
| Auth | JWT + Passport.js + NestJS Guards | Access token (15min) in memory + refresh token (7d) in httpOnly cookie |
| Email | Resend + React Email | Transactional emails: verification, password reset, claim updates, ticket notifications |
| File Upload | DigitalOcean Spaces + Multer | Warranty claim photos, ticket attachments stored with signed URLs |
| Search | Meilisearch (self-hosted) | Parts catalog full-text search with typo tolerance and faceted filters |
| Background Jobs | BullMQ + Redis | Email sending queue, warranty expiry alerts (cron), file scanning |
| Forms | React Hook Form + Zod | Schema-based validation; Zod schemas shared between frontend and API |
| Data Fetching | TanStack Query v5 | Server state, caching, optimistic updates, loading/error states |
| State | Zustand | Client state: auth store, UI preferences, notification state |
| Tables | TanStack Table v8 | Parts catalog grid, ticket list, admin user table with sorting/filtering |
| CMS (optional) | Payload CMS (self-hosted) | Allow non-technical staff to publish case studies without GitHub access |
| Rate Limiting | NestJS ThrottlerModule | API rate limits: 100 req/15min general, 10 req/15min for auth endpoints |
| Validation | class-validator + class-transformer | Every DTO validated at the NestJS pipe level before reaching services |

## Phase 2 — Sprint Breakdown

| Sprint | Tasks & Deliverables | Duration |
| --- | --- | --- |
| Sprint 4 Authentication & Users | - Implement register/login/logout/refresh token endpoints in NestJS - JWT strategy with Passport.js; refresh token rotation with family tracking - Email verification flow with Resend + React Email template - Password reset flow (forgot password → email → reset form) - RBAC guards: @Roles() decorator + RolesGuard on all protected routes - User profile page: view/edit name, email, language preference - Admin: user list, role assignment, active/inactive toggle - Login and register pages in Next.js with React Hook Form + Zod validation - Auth store in Zustand; access token in memory, refresh in httpOnly cookie | 2 weeks |
| Sprint 5 Vehicle Registry | - Vehicle registration form: VIN input, purchase date, mileage - VehicleModel seed data for all current truck models with specs - Vehicle detail page: model specs, purchase info, service history timeline - Vehicle list dashboard: cards view with status indicators - Mileage update feature with audit log - Vehicle ownership transfer flow - Admin: all vehicles list with search and filter by model/status - API endpoints: GET/POST/PATCH /vehicles with ownership scoping - Seed script: populate 5 test vehicles with realistic data for demos | 2 weeks |
| Sprint 6 Warranty Management | - Auto-create warranty records on vehicle registration (from WarrantyType config) - Warranty status dashboard on vehicle page: active warranties with expiry dates - Warranty claim submission form: title, description, mileage, photo upload (DO Spaces) - File upload service: Multer + S3 client, UUID filenames, type/size validation - Engineer claim review UI: claim detail, approve/reject with resolution notes - BullMQ email job: notify customer + engineer on claim status changes - BullMQ cron job: daily warranty expiry check, email 30/60/90 days before - Claim status timeline component showing full history of status changes - Warranty coverage PDF download via signed URL from Spaces | 2 weeks |
| Sprint 7 Parts Catalog | - Parts catalog API: GET /parts with filters (category, model, availability, search query) - Meilisearch index: sync parts on create/update via NestJS lifecycle hook - Parts list page: grid view with TanStack Table, category sidebar filter, availability badge - Parts detail page: description, compatible models, supersession chain, inquiry button - Category tree API and sidebar navigation component - Parts inquiry form: creates a service ticket of type PARTS_REQUEST - Admin: parts CRUD interface with bulk CSV import support - Seed script: 50+ realistic parts with categories and compatibility data - Parts search with typo tolerance: test searching partial part numbers | 2 weeks |
| Sprint 8 Service Tickets | - Ticket creation form: category, title, description, vehicle selector, attachments - Ticket list page: customer sees own tickets; engineer sees assigned tickets; admin sees all - Ticket detail page: status badge, priority indicator, comment thread, file attachments - Comment system: public comments visible to customer; internal notes visible only to engineers - Ticket assignment: engineer/admin can assign to any internal engineer - BullMQ email job: notify on new ticket, assignment change, status change - Ticket number generation: auto-increment with prefix TKT-YYYY-NNNNN - Ticket close/reopen flow with mandatory resolution summary - Mobile-responsive ticket list and detail views | 2 weeks |
| Sprint 9 Admin Dashboard | - Admin dashboard: summary cards (open tickets, active warranties, new users, vehicles registered) - Warranty claim report: claims by status, average resolution time, claims by model - Ticket metrics: open/resolved by category, average first-response time, engineer workload - User management: list, search, role change, deactivate, export CSV - Vehicle management: list all vehicles, flag issues, manually link warranty - System health page: API uptime, DB connection, Redis status, job queue depth - Audit log viewer: track all admin actions (who changed what, when) - Data export: warranties, tickets, parts inquiries as CSV downloads | 2 weeks |
| Sprint 10 Polish & Hardening | - Full mobile responsiveness audit across all portal pages - WCAG 2.1 AA accessibility audit: focus states, ARIA labels, colour contrast - Lighthouse performance audit: LCP <2.5s, CLS <0.1, all pages >85 score - Security audit: verify all endpoints require correct role, test rate limiting - Error boundary components in Next.js for graceful UI error handling - Toast notification system for all success/error feedback - Onboarding flow: guided first-login walkthrough for new customers - Load testing: simulate 100 concurrent users with k6 - Customer acceptance testing with 3 real customers; fix critical feedback | 2 weeks |

## Phase 2 — AI Coding Prompts

🤖 AI CODING PROMPTS — PHASE 2

Prompt 1: Full Auth Module Generate a complete NestJS authentication module with: (1) JWT access token (15min TTL) returned in response body, (2) refresh token (7 day TTL) set as httpOnly cookie, (3) refresh token rotation — each refresh invalidates the old token and issues a new one stored in the RefreshToken Prisma model, (4) token family tracking to detect reuse attacks, (5) Passport.js local strategy for login, JWT strategy for protected routes, (6) endpoints: POST /auth/register, POST /auth/login, POST /auth/refresh, POST /auth/logout, POST /auth/forgot-password, POST /auth/reset-password, GET /auth/me, (7) email verification on register using BullMQ queue and Resend, (8) rate limiting: 10 requests per 15 minutes on all auth endpoints. Use the Prisma schema User and RefreshToken models already defined.

Prompt 2: Parts Catalog + Meilisearch Build a NestJS parts catalog module with Meilisearch integration. The module should: sync parts to Meilisearch on create/update using lifecycle hooks in the PartsService, expose GET /parts with query params: q (search string), categoryId, modelId, availability (enum), page, limit. Return paginated results using the Meilisearch client when q is present (for relevance ranking) and fall back to Prisma for filter-only queries. Include a POST /parts/reindex admin endpoint that clears and rebuilds the Meilisearch index from PostgreSQL. Use the Part and PartCategory Prisma models. Include Swagger documentation.

Prompt 3: Warranty Claim Workflow + BullMQ Implement the full warranty claim workflow in NestJS. Requirements: (1) POST /warranties/:id/claims creates a claim, validates warranty is still ACTIVE and belongs to user's vehicle, uploads attachments to DigitalOcean Spaces via @aws-sdk/client-s3, enqueues an email job to notify the assigned engineer, (2) PATCH /warranties/claims/:id allows INTERNAL_ENGINEER role to update status to APPROVED or REJECTED with resolution text, enqueues email job to notify customer, (3) BullMQ processor for email queue using Resend with React Email templates: one template for claim received, one for claim approved, one for claim rejected, (4) Separate BullMQ cron job running daily at 9am UTC that queries warranties expiring in 30, 60, 90 days and sends reminder emails to vehicle owners.

Prompt 4: Next.js Data Table with TanStack Build a reusable DataTable component in Next.js using TanStack Table v8, TypeScript, and Tailwind/shadcn. Requirements: column definitions passed as props with TypeScript generics, server-side pagination (page/limit passed to API), server-side sorting (sort field + direction passed to API), column-level text filters, row click handler prop, loading skeleton state, empty state component, mobile-friendly card view that swaps in below md breakpoint, CSV export button that downloads current filtered results. Use TanStack Query for data fetching. Show this component used for the Parts Catalog list with columns: Part Number, Name, Category, Compatibility, Availability badge, Price.

Prompt 5: File Upload Service (DO Spaces) Write a NestJS FileUploadService that: (1) accepts a Multer file object, (2) validates type (whitelist: image/jpeg, image/png, image/webp, application/pdf) and size (max 10MB), (3) generates a UUID-based key: uploads/{entityType}/{entityId}/{uuid}.{ext}, (4) uploads to DigitalOcean Spaces using @aws-sdk/client-s3 with PutObjectCommand, (5) stores the URL in the Attachment Prisma model with filename, mimeType, sizeBytes, (6) exposes a method getSignedUrl(key, expiresIn) using GetObjectCommand + getSignedUrl from @aws-sdk/s3-request-presigner, (7) file URLs in API responses always return fresh signed URLs with 1-hour expiry. Wire this service into the WarrantyClaim and Ticket modules.

## Phase 2 — Estimated Development Time

| Total Calendar Time | 16 weeks (8 x 2-week sprints, Weeks 9–24) |
| --- | --- |

| Effective Dev Hours | ~320 hours (20 hrs/week) |
| --- | --- |

| AI Tool Leverage | ~65% generated by Claude Code (CRUD modules, DTOs, tests, email templates) |
| --- | --- |

| Human Focus Hours | ~112 hours on UX flows, business logic edge cases, customer testing |
| --- | --- |

| Infrastructure Cost | ~$55/month (Droplet $24 + DB $15 + Spaces $5 + Resend $0-20) |
| --- | --- |

## Phase 2 — Deliverables

| ✓ | Authenticated aftersales portal at app.yourdomain.com with customer, engineer, and admin roles |
| --- | --- |
| ✓ | Vehicle registry: customers can register trucks by VIN and view full vehicle profiles |
| ✓ | Warranty management: digital warranty records, claim submission, engineer approval workflow |
| ✓ | Parts catalog: 500+ indexed parts with Meilisearch full-text search and model compatibility |
| ✓ | Service ticket system: full lifecycle from creation to resolution with email notifications |
| ✓ | Admin dashboard with reporting: claims by status, ticket resolution metrics, user activity |
| ✓ | Passing load test: 100 concurrent users without degradation |
| ✓ | 3+ real customers actively using the portal |

## Phase 2 — Risks and Mitigation

| Risk | Severity | Impact | Mitigation |
| --- | --- | --- | --- |
| Scope creep on ticket system | High | Tickets become a 6-week module and delay admin dashboard | Hard cap: ticket comments + file upload is done. No SLA tracking, no escalation rules, no Kanban board until Phase 3+ based on customer demand. |
| File upload edge cases (large files, corrupted images) | Medium | Customer frustration, potential server memory issues | Client-side validation before upload. Multer size limit at NestJS. Use multipart streaming, not buffering. |
| Meilisearch index drift (parts updated but not re-indexed) | Medium | Search results show stale data | Implement a nightly reindex cron job as a safety net. Add index drift monitoring alert. |
| Email deliverability issues with Resend | Medium | Customers miss critical warranty and ticket notifications | Configure SPF, DKIM, DMARC records from day one. Monitor bounce rates in Resend dashboard. Have fallback SMS via Twilio ready. |
| JWT refresh token vulnerabilities | High | Account takeover if refresh tokens are leaked or reused | Implement token family invalidation (whole family invalidated on reuse detection). Always httpOnly cookie for refresh token. Regular rotation enforced. |
| RBAC gaps: customer accessing other customer data | High | Data breach, legal liability | Every service method checks ownership: query always scoped by userId. Write integration tests specifically for cross-user access attempts. |

| PHASE 3 | FleetOS Foundation Add real-time vehicle telemetry, fleet dashboards, fault monitoring, and SaaS billing — Weeks 25 to 36 |
| --- | --- |

Phase 3 transforms the platform from a support tool into an operations platform. By now you have real vehicles in the field, real data from customer interactions, and a foundation of auth, vehicles, and warranties. FleetOS layers real-time telemetry on top of this foundation — and turns the platform into a recurring revenue SaaS product.

## Phase 3 — Objectives

- Deploy MQTT broker (EMQX) to ingest telemetry from vehicle OBD gateways

- Activate TimescaleDB extension on existing PostgreSQL for time-series telemetry storage

- Build a real-time fleet dashboard: GPS location, battery SOC, speed, fault codes

- Build fault code monitoring with configurable alerts (email + optional WhatsApp)

- Build predictive maintenance rules engine (rule-based, not ML at this stage)

- Implement multi-tenant fleet organisations and Stripe subscription billing

## Phase 3 — Required Technologies

| Layer | Technology | Purpose |
| --- | --- | --- |
| MQTT Broker | EMQX (Docker, open-source) | Handles MQTT connections from vehicle gateways; routes to telemetry service |
| Time-Series DB | TimescaleDB (PostgreSQL extension) | Hypertable on vehicle_telemetry; automatic partitioning, compression, retention |
| Real-Time Push | Server-Sent Events (NestJS) | Push telemetry updates to fleet dashboard without polling; simpler than WebSockets |
| Maps | Mapbox GL JS (or Leaflet + OSM) | Fleet map with vehicle markers; route history; geofencing zones |
| Charts | Recharts + TanStack Query | Battery SOC history, range estimates, mileage trends on vehicle dashboards |
| Billing | Stripe (Subscriptions + Webhooks) | SaaS tier management: Starter/Growth/Scale; usage-based metering in Phase 4 |
| WhatsApp Alerts | Twilio WhatsApp Business API | Critical fault alerts to fleet managers; essential for SE Asia market |
| Multi-Tenancy | PostgreSQL schema isolation | Each fleet org gets own schema; shared parts catalog in public schema |
| Vehicle Gateway | Raspberry Pi + OBD-II adapter (reference hw) | Reference hardware for telemetry gateway; customers can use compatible devices |
| Telemetry Protocol | MQTT 3.1.1 + JSON payload | Lightweight, widely supported; JSON payload with SOC, speed, GPS, fault codes |
| Job Processing | BullMQ (extended) | Telemetry aggregation jobs, maintenance rule evaluation, alert dispatch |
| Analytics (future) | ClickHouse stub | Schema-ready for fleet analytics; not deployed until >5000 vehicle-days of data |

## Phase 3 — Sprint Breakdown

| Sprint | Tasks & Deliverables | Duration |
| --- | --- | --- |
| Sprint 11 Telemetry Infrastructure | - Deploy EMQX broker in Docker Compose on a dedicated 2GB Droplet ($18/mo) - Enable TimescaleDB extension: CREATE EXTENSION timescaledb on existing DB - Create vehicle_telemetry table and convert to hypertable partitioned by timestamp - Add compression policy (compress chunks older than 7 days) - Add retention policy (drop raw data older than 1 year; keep hourly aggregates) - Write NestJS TelemetryModule: MQTT client subscribes to vehicle/+/telemetry topic - Write telemetry ingest endpoint: validate, transform, insert to TimescaleDB via Prisma $queryRaw - Simulate telemetry with a Node.js script publishing mock data for 5 test vehicles - Verify ingestion rate: confirm 100 messages/second sustained without DB lock contention | 2 weeks |
| Sprint 12 Fleet Dashboard | - Fleet organisation model: Org -> Fleet -> Vehicle hierarchy in schema - Fleet dashboard page: vehicle cards grid showing real-time SOC, speed, status - Server-Sent Events endpoint GET /fleet/:id/stream using NestJS EventEmitter + SSE - Next.js useFleetSSE hook consuming SSE stream and updating Zustand fleet store - Mapbox integration: live vehicle markers on map with click-to-vehicle-detail - Vehicle detail telemetry page: last 24h charts for SOC, speed, odometer - Fleet summary stats: total vehicles, online/offline count, average SOC, alerts count - Mobile-responsive fleet dashboard: card view on mobile, map on desktop - Lazy-load fleet data: paginate vehicles, only stream top 20 by last activity | 2 weeks |
| Sprint 13 Fault Monitoring & Alerts | - DTC (fault code) library: seed 50 common EV fault codes with descriptions and severity - Active fault tracking: store current active DTCs per vehicle in vehicle_faults table - Fault alert rules: configurable threshold rules per fault code (e.g., P0A80 battery fault = Critical) - Alert dispatch service: BullMQ job triggers email + WhatsApp on new Critical fault - Twilio WhatsApp integration: send fault alert to fleet manager phone number - Fleet manager alerts settings page: configure which fault codes trigger notifications - Fault history timeline on vehicle detail page: all historical faults with timestamps - Fault code search in documentation: link from DTC in dashboard to Docusaurus troubleshooting page - Alert deduplication: suppress repeat alerts for same fault within 1-hour window | 2 weeks |
| Sprint 14 Predictive Maintenance | - Maintenance schedule model: service_intervals table (e.g., brake check every 20,000km) - Interval tracking: compare vehicle current_mileage against next_service_due - Predictive alert: when mileage within 10% of next service, create maintenance ticket automatically - Battery health scoring: simple rule-based score from charge cycle count and SOC variance - Range estimation: rolling average of kWh/km from last 30 days of telemetry - Maintenance dashboard: list all vehicles with upcoming service in next 30/60/90 days - Fleet manager can acknowledge maintenance alerts and schedule service appointments - Maintenance cost tracker: log parts and labour costs against completed service records - Weekly maintenance summary email: dispatched every Monday for fleet managers | 2 weeks |
| Sprint 15 Multi-Tenancy + Billing | - Organisation onboarding flow: create org, invite team members, assign vehicles to fleet - PostgreSQL schema isolation: middleware that sets search_path per request based on org slug - Stripe products and prices setup: Starter ($99), Growth ($499), Scale ($1999) per month - Stripe Checkout flow: org admin selects plan, redirected to Stripe hosted checkout - Stripe webhook handler: subscription.created, subscription.updated, subscription.deleted - Plan enforcement middleware: check org subscription tier before serving FleetOS features - Billing portal: org admin can view invoices, update payment method, change plan via Stripe Portal - Trial period: 14-day free trial with all Growth features; auto-downgrade to Starter on expiry - Subscription analytics: MRR calculation, churn tracking in admin dashboard | 2 weeks |
| Sprint 16 FleetOS Polish & Launch | - Fleet onboarding wizard: guided flow to add first vehicle and configure telemetry gateway - Gateway setup documentation: step-by-step guide for connecting OBD-II device to EMQX broker - Performance testing: simulate 500 vehicles sending telemetry; confirm dashboard remains responsive - Security audit: verify tenant isolation (org A cannot access org B data), penetration test MQTT broker - DigitalOcean server upgrade: scale App Server to 8GB RAM / 4 vCPU ($48/mo) - Scale managed PostgreSQL to 4GB RAM plan ($50/mo) - Set up Grafana alerts: notify on DB CPU >80%, MQTT broker connection drops, API p99 latency >1s - FleetOS product hunt launch preparation: screenshots, demo video, changelog - Onboard first paying FleetOS customer on Growth plan | 2 weeks |

## Phase 3 — AI Coding Prompts

🤖 AI CODING PROMPTS — PHASE 3

Prompt 1: TimescaleDB Telemetry Ingest Write a NestJS TelemetryModule that: (1) subscribes to MQTT topic vehicle/+/telemetry using the mqtt npm package, where + is the vehicleId, (2) validates the incoming JSON payload against a TelemetryPayloadDto: { soc: number (0-100), speedKmh: number, odometer: number, latitude: number, longitude: number, faultCodes: string[], batteryTempC: number, timestamp: ISO string }, (3) inserts valid payloads into the vehicle_telemetry TimescaleDB hypertable using Prisma $executeRaw to avoid ORM overhead on high-frequency inserts, (4) updates a vehicle_last_seen Redis key with TTL 5 minutes to track online status, (5) emits a telemetry.received NestJS event for downstream consumers (dashboard SSE, fault checker). Include error handling for malformed payloads and disconnected MQTT broker with reconnection backoff.

Prompt 2: Server-Sent Events Fleet Stream Implement a real-time fleet dashboard stream in NestJS using Server-Sent Events. Build: (1) GET /fleet/:fleetId/stream endpoint using @Sse() decorator that streams MessageEvent objects, (2) uses NestJS EventEmitter to receive telemetry.received events filtered by fleetId, (3) emits vehicle position and SOC updates as SSE data: { vehicleId, soc, speedKmh, latitude, longitude, isOnline }, (4) sends a heartbeat event every 30 seconds to keep the connection alive, (5) cleans up EventEmitter listener on client disconnect. Then write a Next.js custom hook useFleetStream(fleetId) using EventSource API that subscribes to the SSE endpoint, updates a Zustand fleet store, and handles reconnection with exponential backoff.

Prompt 3: Stripe Subscription + Webhooks Implement Stripe subscription billing in NestJS. Requirements: (1) POST /billing/create-checkout-session creates a Stripe Checkout Session for the selected plan (Starter, Growth, Scale), sets metadata: { organizationId }, returns the checkout URL, (2) POST /billing/webhook handles Stripe webhook events: checkout.session.completed sets org subscription status to ACTIVE and tier to selected plan, customer.subscription.updated updates tier on plan change, customer.subscription.deleted downgrades to free tier, (3) a SubscriptionGuard that checks the org subscription tier against the required minimum tier for FleetOS features, returning 402 with upgrade prompt if insufficient, (4) POST /billing/portal creates a Stripe Customer Portal session for self-service plan management. Use Stripe Node.js SDK v14. Store subscription data in the Organization Prisma model.

Prompt 4: Predictive Maintenance Engine Build a rule-based predictive maintenance engine as a NestJS service. Requirements: (1) A ServiceInterval Prisma model with fields: vehicleModelId, componentName, intervalKm, intervalMonths, description, (2) A MaintenanceStatus service that for a given vehicle, computes: kmUntilNextService (current_odometer vs last service + intervalKm), daysUntilNextService (last service date + intervalMonths), healthScore (0-100 composite of: km remaining as % of interval, days remaining as % of interval), (3) A BullMQ cron job running nightly that: fetches all active vehicles, computes maintenance status for each, creates a Ticket of category MAINTENANCE_DUE if healthScore < 20 and no open maintenance ticket exists, sends a summary email to fleet manager if any vehicle has healthScore < 20, (4) A GET /fleet/:id/maintenance endpoint returning maintenance status for all vehicles in the fleet, sorted by healthScore ascending.

## Phase 3 — Estimated Development Time

| Total Calendar Time | 12 weeks (6 x 2-week sprints, Weeks 25–36) |
| --- | --- |

| Effective Dev Hours | ~240 hours (20 hrs/week) |
| --- | --- |

| AI Tool Leverage | ~55% generated by Claude Code (telemetry pipeline, Stripe integration, SSE streams) |
| --- | --- |

| Human Focus Hours | ~108 hours on hardware integration, tenant architecture, customer pilots |
| --- | --- |

| Infrastructure Cost | $153/month at scale (upgraded Droplet + DB + MQTT server) |
| --- | --- |

| Revenue Target | 5 x Growth plan customers = $2,495 MRR by end of Phase 3 |
| --- | --- |

## Phase 3 — Deliverables

| ✓ | Live MQTT telemetry ingestion: vehicle data flowing into TimescaleDB from real vehicles |
| --- | --- |
| ✓ | Real-time fleet dashboard: map + status cards updating live for all fleet vehicles |
| ✓ | Fault monitoring: Critical DTCs trigger WhatsApp and email alerts to fleet managers |
| ✓ | Predictive maintenance: automatic maintenance tickets created based on mileage and time rules |
| ✓ | Multi-tenant SaaS: fleet organisations with isolated data and Stripe subscription billing |
| ✓ | First paying customer on FleetOS Growth plan ($499/month) |
| ✓ | Platform sustaining $2,000+ MRR covering all infrastructure costs |

## Phase 3 — Risks and Mitigation

| Risk | Severity | Impact | Mitigation |
| --- | --- | --- | --- |
| Hardware integration complexity | High | MQTT broker works but no vehicles can actually connect | Build a software simulator first. Confirm MQTT protocol with hardware vendor before Sprint 11. Use EMQX dashboard to debug connection issues. |
| TimescaleDB performance under load | Medium | Dashboard queries slow when telemetry table has >10M rows | Create continuous aggregates (hourly/daily) on insert. Dashboard queries always hit aggregates, never raw data for >24h windows. |
| Tenant isolation failure | High | Data breach: org A sees org B vehicle data | Write integration tests that explicitly attempt cross-tenant access. Penetration test before first paying customer. Row-level security as backup layer. |
| Stripe webhook replay attacks | Medium | Subscription events processed multiple times causing billing errors | Check Stripe-Signature header on every webhook. Store processed event IDs in Redis for 24h idempotency check. |
| WhatsApp Business API approval delay | Medium | Alert notifications unavailable at launch | Apply for WhatsApp Business API in Week 20 (Sprint 8). Email alerts as fallback. SMS via Twilio as secondary fallback. |
| GPS data privacy regulations (Indonesia / China) | High | Legal risk from storing vehicle location data | Store GPS as geohash precision 6 (150m accuracy) in logs; only full precision in 5min rolling window. Add explicit data consent in onboarding. Consult local legal counsel before launch. |

# Master Timeline Overview

The complete 36-week roadmap from infrastructure setup to first paying FleetOS customer.

| Week | Milestone & Activity |
| --- | --- |
| Wk 1–2 | PHASE 1 — Sprint 0: TrueNAS services running, monorepo created, docker-compose.dev.yml working, CLAUDE.md written, prod infra provisioned |
| Wk 3–4 | PHASE 1 — Sprint 1: Three-layer doc structure scaffolded, T7-134L manuals assembled, EN/ZH/ID language switcher live at docs.yourdomain.com |
| Wk 5–6 | PHASE 1 — Sprint 2: Next.js marketing homepage + NestJS API skeleton with Swagger live |
| Wk 7–8 | PHASE 1 — Sprint 3: SEO, analytics, monitoring, Lighthouse >85, first customer onboarded to docs |
| Wk 9–10 | PHASE 2 — Sprint 4: Full auth system live: register, login, roles, email verification, password reset |
| Wk 11–12 | PHASE 2 — Sprint 5: Vehicle registry live — customers can register trucks and view vehicle profiles |
| Wk 13–14 | PHASE 2 — Sprint 6: Warranty system live — digital warranty records, claim submission, engineer review |
| Wk 15–16 | PHASE 2 — Sprint 7: Parts catalog live with Meilisearch — 500+ searchable parts with compatibility filter |
| Wk 17–18 | PHASE 2 — Sprint 8: Service tickets live — creation, assignment, comments, email notifications |
| Wk 19–20 | PHASE 2 — Sprint 9: Admin dashboard with reporting, user management, data export |
| Wk 21–24 | PHASE 2 — Sprint 10: Mobile polish, accessibility, load testing, 3 real customers using portal |
| Wk 25–26 | PHASE 3 — Sprint 11: EMQX MQTT broker + TimescaleDB live, mock telemetry ingesting at 100 msg/sec |
| Wk 27–28 | PHASE 3 — Sprint 12: Real-time fleet dashboard with SSE stream, Mapbox vehicle markers, SOC charts |
| Wk 29–30 | PHASE 3 — Sprint 13: Fault monitoring + WhatsApp alerts for Critical DTCs |
| Wk 31–32 | PHASE 3 — Sprint 14: Predictive maintenance engine with automated service ticket creation |
| Wk 33–34 | PHASE 3 — Sprint 15: Multi-tenant orgs + Stripe billing (Starter/Growth/Scale tiers) |
| Wk 35–36 | PHASE 3 — Sprint 16: FleetOS launch, first paying customer, $2,000+ MRR target |

# Claude Code Development Workflow

## The Daily Development Rhythm

A disciplined daily workflow maximises the leverage AI tools provide. The goal is to spend your cognitive budget on decisions only a human can make: architecture trade-offs, customer conversations, UX judgment. Let AI handle the rest.

| Time | Activity |
| --- | --- |
| 30 min | Morning: Review yesterday's code. Fix failing tests. Check Sentry errors. Write today's 3 tasks in a note. Start Claude Code with: 'Read CLAUDE.md, then let's continue from where we left off.' |
| 3 hours | Deep work block 1: Build the primary feature. Claude Code runs autonomously — writes files, runs migrations, executes tests. You review output and make decisions. |
| 30 min | Midday: Commit progress. Push to local staging (TrueNAS or workstation). Take a break — subconscious resolves blockers. |
| 3 hours | Deep work block 2: Integration, test-writing, polish. Ask Claude Code to write Jest tests for this morning's code. Fix edge cases it flags. |
| 30 min | End of day: Review Claude Code's changes via git diff. Update sprint board. Write tomorrow's 3 tasks. Push to main branch. |

## AI Tool Selection by Task

| Layer | Technology | Purpose |
| --- | --- | --- |
| NestJS modules | Claude Code (primary) | Give it the Prisma model; it writes controller/service/DTO/guard/tests directly to your repo files |
| Architecture decisions | Claude (chat) | Long context; maintains architecture decisions across planning sessions |
| UI components | v0.dev → Claude Code | v0 generates shadcn component visually; Claude Code wires it to your API with full TypeScript types |
| Database schemas | Claude Code | Describe requirements in plain English; it writes Prisma schema, runs migrations, creates seed data |
| Doc translation | Claude Code | Translates MDX partials (_shared/_partials/) to ZH/ID preserving all component tags |
| Unit tests | Claude Code | Pass it a service file; it writes a full Jest test suite covering happy paths and edge cases |
| Debugging | Claude Code | Point it at failing tests or Sentry errors; it diagnoses root cause and applies the fix autonomously |
| Code review | Claude (chat) | Paste git diff; reviews for security gaps, logic errors, and architecture drift |

## The CLAUDE.md File — Persistent Project Context

Claude Code reads CLAUDE.md automatically at the start of every session. This file replaces .cursorrules and gives Claude Code persistent knowledge of your architecture, conventions, and project context — eliminating repetitive context-setting and keeping all generated code consistent.

# CLAUDE.md — EV Truck Platform ## Project Overview NestJS + Next.js + Docusaurus monorepo for an EV truck aftersales platform. Dev DB/Storage: TrueNAS Scale at 192.168.1.100 (PostgreSQL:5432, MinIO:9000). Prod: DigitalOcean Droplet + Managed PostgreSQL + Spaces. ## Code Conventions TypeScript strict mode. async/await only — no raw Promises. Business logic in services only. Controllers: parse -> call -> return. Validate all DTOs. Wrap all responses in TransformInterceptor envelope. JWT guard + RolesGuard on every protected endpoint. Never expose passwordHash. ## Documentation Layer Rules _shared/_partials/ -> content for ALL T7 trucks (charging, safety, cab, warranty) platforms/t7-{90,90l,134l,169l}/ -> battery variant content applications/{arm-roll,dumper,compactor,sweeper}/ -> body type content manuals/{platform}-{body}/ -> thin MDX import assembly files Preserve all MDX tags when translating to ZH or ID.

# Infrastructure Cost Summary

| Service | Phase 1 | Phase 2 | Phase 3 (FleetOS) |
| --- | --- | --- | --- |
| App Server (DigitalOcean Droplet) | $24 | $24 | $48 |
| Managed PostgreSQL (DO) | $15 | $15 | $50 |
| MQTT Broker (separate Droplet) | — | — | $18 |
| Object Storage (DO Spaces) | $5 | $5 | $10 |
| Cloudflare CDN / WAF | $0 | $0 | $20 |
| Email (Resend) | $0 | $0–20 | $20 |
| Domain Name | $1 | $1 | $1 |
| Monitoring (Grafana) | $0 | $0 | $0 |
| Error Tracking (Sentry) | $0 | $0 | $0 |
| Secrets (Doppler) | $0 | $0 | $0 |
| CI/CD (GitHub Actions) | $0 | $0 | $0 |
| MONTHLY TOTAL | ~$45 | ~$65 | ~$167 |

Cost philosophy: At 5 paying FleetOS customers on the Growth plan ($499/month), monthly revenue reaches $2,495. Infrastructure at that point costs ~$167/month. Infrastructure as a percentage of revenue = 6.7% — well within healthy SaaS norms. Every dollar of infrastructure cost added in Phase 3 should be justified by a corresponding revenue milestone.

# Closing: The Founder's Compass

Three principles will determine whether this succeeds:

1. Ship to customers, not to architecture. The documentation portal is more valuable than the perfectly-designed API. Get something in front of a real customer at the end of every sprint, even if it is incomplete. Customer feedback is the only reliable signal.

2. Use AI as a force multiplier, not a replacement for judgment. AI tools generate code fast, but they do not know your customers, your constraints, or your competitive landscape. Use them to eliminate the work that does not require judgment, so you can focus on the work that does.

3. Complexity is debt. Every module you build before a customer asks for it is a liability. The FleetOS features in Phase 3 should only be built if Phase 2 customers are asking for them. If they are not, stay in Phase 2 and make it exceptional.

End of Document  •  EV Truck Platform  •  Solo Founder Execution Plan  •  v1.0  •  March 2026